Chronogramme du stage — PlantUML

Projet : Parc Informatique MFA

Document associé : CHAPITRE_5_ANALYSE_CONCEPTUELLE.md

Ce fichier contient le code PlantUML du chronogramme (diagramme de Gantt) du stage.

Il couvre : analyse de l’existant, proposition du thème, analyse conceptuelle, installation des outils, sprints / fonctionnalités, tests, et rédaction du mémoire en parallèle.

Comment générer l’image

Copier le bloc @startgantt … @endgantt dans PlantUML online

Ou ouvrir CHRONOGRAMME_STAGE.puml avec l’extension PlantUML (VS Code / IntelliJ)

Ou en CLI : plantuml docs/CHRONOGRAMME_STAGE.puml

Les dates sont illustratives (semestre de stage). À ajuster selon ton calendrier réel.

────────────────────────────────────────

Code PlantUML

Le même code est dans CHRONOGRAMME_STAGE.puml :

@startgantt
title Chronogramme du stage — SI Parc Informatique MFA
printscale weekly
saturday are closed
sunday are closed

Project starts 2026-02-02

'======== Légende des couleurs ========
' Bleu   : cadrage / analyse
' Orange : outillage
' Vert   : sprints de développement
' Violet : tests / recette
' Gris   : rédaction mémoire (parallèle)

'======== Phase cadrage ========
-- Cadrage --
[Analyse de l'existant] as AE lasts 15 days
AE starts 2026-02-02
AE is colored in DeepSkyBlue

[Proposition du thème de stage] as PT lasts 8 days
PT starts at AE's end
PT is colored in CornflowerBlue

[Analyse conceptuelle (Scrum, backlog, UML)] as AC lasts 18 days
AC starts at PT's end
AC is colored in RoyalBlue

'======== Outillage ========
-- Installation & cadrage technique --
[Installation des outils (Node, PostgreSQL, Git, IDE)] as OUT lasts 7 days
OUT starts 2026-03-02
OUT is colored in DarkOrange

[Mise en place projet (repo, BDD, CI locale)] as MP lasts 7 days
MP starts at OUT's end
MP is colored in Orange

'======== Releases / Sprints ========
-- Développement — Release 1 Socle --
[Sprint 1 — Authentification & profil] as S1 lasts 10 days
S1 starts 2026-03-16
S1 is colored in MediumSeaGreen

[Sprint 2 — Utilisateurs, services, catégories] as S2 lasts 10 days
S2 starts at S1's end
S2 is colored in MediumSeaGreen

[Sprint 3 — Inventaire matériels] as S3 lasts 10 days
S3 starts at S2's end
S3 is colored in MediumSeaGreen

-- Développement — Release 2 Interventions --
[Sprint 4 — Affectations] as S4 lasts 10 days
S4 starts at S3's end
S4 is colored in SeaGreen

[Sprint 5 — Tickets (création, workflow, PJ)] as S5 lasts 10 days
S5 starts at S4's end
S5 is colored in SeaGreen

[Sprint 6 — Notifications] as S6 lasts 10 days
S6 starts at S5's end
S6 is colored in SeaGreen

-- Développement — Release 3 Pilotage --
[Sprint 7 — Maintenances] as S7 lasts 10 days
S7 starts at S6's end
S7 is colored in ForestGreen

[Sprint 8 — Dashboard KPI, pilotage & SLA] as S8 lasts 10 days
S8 starts at S7's end
S8 is colored in ForestGreen

-- Développement — Release 4 Conformité --
[Sprint 9 — Rapports PDF/Excel & journal d'audit] as S9 lasts 10 days
S9 starts at S8's end
S9 is colored in DarkGreen

[Sprint 10 — Seeds démo, polish UI, doc] as S10 lasts 10 days
S10 starts at S9's end
S10 is colored in DarkGreen

'======== Qualité ========
-- Tests & recette --
[Tests unitaires / API (au fil des sprints)] as TST lasts 70 days
TST starts 2026-03-23
TST is colored in MediumPurple

[Recette fonctionnelle & correctifs] as REC lasts 12 days
REC starts at S10's end
REC is colored in BlueViolet

[Préparation démonstration / soutenance] as DEMO lasts 8 days
DEMO starts at REC's end
DEMO is colored in SlateBlue

'======== Mémoire (parallèle sur toute la durée) ========
-- Rédaction du mémoire (parallèle) --
[Rédaction mémoire — introduction & existant] as M1 lasts 25 days
M1 starts 2026-02-09
M1 is colored in Gray

[Rédaction mémoire — analyse conceptuelle] as M2 lasts 25 days
M2 starts 2026-03-09
M2 is colored in Gray

[Rédaction mémoire — réalisation & sprints] as M3 lasts 55 days
M3 starts 2026-04-06
M3 is colored in DarkGray

[Rédaction mémoire — tests, conclusion, relecture] as M4 lasts 30 days
M4 starts 2026-06-01
M4 is colored in DimGray

[Finalisation mémoire & annexes] as M5 lasts 12 days
M5 starts at DEMO's start
M5 is colored in Black

@endgantt

────────────────────────────────────────

Lecture du chronogramme

| Phase | Contenu |
| --- | --- |
| Analyse de l’existant | Étude du MFA, processus inventaire / interventions, limites du système actuel |
| Proposition du thème | Validation du sujet « Parc Informatique & interventions » |
| Analyse conceptuelle | Scrum, Product Backlog, user stories, dictionnaire, UML (ch. 5) |
| Installation des outils | Node.js, PostgreSQL, Git, IDE, extensions |
| Sprints 1→10 | Livraison incrémentale des fonctionnalités (R1→R4) |
| Tests | Continus pendant le développement + recette finale |
| Mémoire | Rédaction en parallèle dès le cadrage jusqu’à la soutenance |

Ajuste les dates Project starts et les durées lasts X days pour coller à ton calendrier de stage réel.